| PSP2.1 Process Script |  |
| --- | --- |
| Purpose | - To guide the development of module-level programs |
| Entry Criteria | - Problem description - PSP2.1 Project Plan Summary form - Size Estimating template - Historical size and time data (estimated and actual) - Time and Defect Recording logs - Defect Type, Coding, and Size Counting standards - Stopwatch (optional) |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Planning | - Produce or obtain a requirements statement. - Use the PROBE method to estimate the added and modified size and the size prediction interval of this program. - Complete the Size Estimating template. - Use the PROBE method to estimate the required development time and the time prediction interval. - Complete a Task Planning template. - Complete a Schedule Planning template. - Enter the plan data in the Project Plan Summary form. - Complete the Time Recording log. |
| 2 | Development | - Design the program. - Document the design in the design templates. - Review the design, and fix and log all defects found. - Implement the design. - Review the code, and fix and log all defects found. - Compile the program, and fix and log all defects found. - Test the program, and fix and log all defects found. - Complete the Time Recording log. |
| 3 | Postmortem | - Complete the Project Plan Summary form with actual time, defect, and size data. |

| Exit Criteria | - A thoroughly tested program - Completed Project Plan Summary form with estimated and actual data - Completed Size Estimating and Task and Schedule Planning templates - Completed Design templates - Completed Design Review and Code Review checklists - Completed Test Report template - Completed PIP forms - Completed Time and Defect Recording logs |
| --- | --- |

| PSP2.1 Planning Script |  |
| --- | --- |
| Purpose | - To guide the PSP planning process |
| Entry Criteria | - Problem description - PSP2.1 Project Plan Summary form - Size Estimating, Task Planning, and Schedule Planning templates - Historical size and time data (estimated and actual) - Time Recording log |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Program Requirements | - Produce or obtain a requirements statement for the program. - Ensure that the requirements statement is clear and unambiguous. - Resolve any questions. |
| 2 | Size Estimate | - Produce a program conceptual design. - Use the PROBE method to estimate the added and modified size of this program. - Complete the Size Estimating template and Project Plan Summary form. - Calculate the 70% size prediction interval. (Note: This step is completed by the SEI student workbook) |
| 3 | Resource Estimate | - Use the PROBE method to estimate the time required to develop this program. - Calculate the 70% size prediction interval. ((Note: This step is completed by the SEI student workbook.) - Using the To Date % from the most recently developed program as a guide, distribute the development time over the planned project phases. (Note: This step is completed by the SEI student workbook.) |
| 4 | Task and Schedule Planning | For projects lasting several days or more, complete the Task Planning and Schedule Planning templates. |
| 5 | Defect Estimate | - Based on your to-date data on defects per added and modified size unit, estimate the total defects to be found in this program. - Based on your To Date % data, estimate the number of defects to be injected and removed by phase. |

| Exit Criteria | - Documented requirements statement - Program conceptual design - Completed Size Estimating template - For projects lasting several days or more, completed Task and Schedule Planning templates - Completed Project Plan Summary form with estimated program size, development time, and defect data, and the time and size prediction intervals - Completed Time Recording log |
| --- | --- |

| PSP2.1 Development Script |  |
| --- | --- |
| Purpose | - To guide the development of small programs |
| Entry Criteria | - Requirements statement - Project Plan Summary form with estimated program size and development time - For projects lasting several days or more, completed Task Planning and Schedule Planning templates - Time and Defect Recording logs - Defect Type standard and Coding standard |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Design | - Review the requirements and produce an external specification to meet them. - Complete Functional and Operational Specification templates to record this specification. - Produce a design to meet this specification. - Record the design in Functional, Operational, State, and Logic Specification templates. - Record in the Defect Recording log any requirements defects found. - Record time in the Time Recording log. |
| 2 | Design Review | - Follow the Design Review script and checklist and review the design. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. |
| 3 | Code | - Implement the design following the Coding standard. - Record in the Defect Recording log any requirements or design defects found. - Record time in the Time Recording log. |
| 4 | Code Review | - Follow the Code Review script and checklist and review the code. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. |
| 5 | Compile | - Compile the program until there are no compile errors. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. |
| 6 | Test | - Test until all tests run without error. - Fix all defects found. - Record defects in the Defect Recording log. - Record time in the Time Recording log. - Complete a Test Report template on the tests conducted and the results obtained. |

| Exit Criteria | - A thoroughly tested program that conforms to the Coding standard - Completed Design templates - Completed Design Review and Code Review checklists - Completed Test Report template - Completed Time and Defect Recording logs |
| --- | --- |

| PSP2.1 Design Review Script |  |
| --- | --- |
| Purpose | To guide you in reviewing detailed designs |
| Entry Criteria | - Completed program design documented with the PSP Design templates - Design Review checklist - Design standard - Defect Type standard - Time and Defect Recording logs |
| General | Where the design was previously verified, check that the analyses - covered all of the design - were updated for all design changes - are correct - are clear and complete |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Preparation | - Examine the program and checklist and decide on a review strategy. - Examine the program to identify its state machines, internal loops, and variable and system limits. - Use a trace table or other analytical method to verify the correctness of the design. |
| 2 | Review | - Follow the Design Review checklist. - Review the entire program for each checklist category; do not try to review for more than one category at a time! - Check off each item as you complete it. - Complete a separate checklist for each product or product segment reviewed. |
| 3 | Fix Check | - Check each defect fix for correctness. - Re-review all changes. - Record any fix defects as new defects and, where you know the defective defect number, enter it in the fix defect space. |

| Exit Criteria | - A fully reviewed detailed design - One or more Design Review checklists for every design reviewed - Documented design analysis results - All identified defects fixed and all fixes checked - Completed Time and Defect Recording logs |
| --- | --- |

| PSP2.1 Postmortem Script |  |
| --- | --- |
| Purpose | - To guide the PSP postmortem process |
| Entry Criteria | - Problem description and requirements statement - Project Plan Summary form with program size, development time, and defect data - For projects lasting several days or more, completed Task Planning and Schedule Planning templates - Completed Test Report template - Completed Design templates - Completed Design Review and Code Review checklists - Completed Time and Defect Recording logs - A tested and running program that conforms to the coding and size counting standards |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Defect Recording | - Review the Project Plan Summary to verify that all of the defects found in each phase were recorded. - Using your best recollection, record any omitted defects. |
| 2 | Defect Data Consistency | - Check that the data on every defect in the Defect Recording log are accurate and complete. - Verify that the numbers of defects injected and removed per phase are reasonable and correct. - Determine the process yield and verify that the value is reasonable and correct. - Using your best recollection, correct any missing or incorrect defect data. |
| 3 | Size | - Count the size of the completed program. - Determine the size of the base, deleted, modified, base additions, reused, new reusable code, and added parts. - Enter these data in the Size Estimating template. - Determine the total program size - Enter this data in the Project Plan Summary form. |
| 4 | Time | - Review the completed Time Recording log for errors or omissions. - Using your best recollection, correct any missing or incomplete time data. |

| Exit Criteria | - A thoroughly tested program that conforms to the coding and size counting standards - Completed Design templates - Completed Design Review and Code Review checklists - Completed Test Report template - Completed Project Plan Summary form - Completed PIP forms describing process problems, improvement suggestions, and lessons learned - Completed Time and Defect Recording logs |
| --- | --- |

| PROBE Estimating Script |  |
| --- | --- |
| Purpose | - To guide the size and time estimating process using the PROBE method |
| Entry Criteria | - Requirements statement - Size Estimating template and instructions - Size per item data for part types - Time Recording log - Historical size and time data |
| General | - This script assumes that you are using added and modified size data as the size-accounting types for making size and time estimates. - If you choose some other size-accounting types, replace every “added and modified” in this script with the size-accounting types of your choice. |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Conceptual Design | Review the requirements and produce a conceptual design. |
| 2 | Parts Additions | Follow the Size Estimating Template instructions to estimate the parts additions and the new reusable parts sizes. |
| 3 | Base Parts and Reused Parts | - For the base program, estimate the size of the base, deleted, modified, and added code. - Measure and/or estimate the size of the parts to be reused. |
| 4 | Size Estimating Procedure | - If you have sufficient estimated proxy size and actual added and modified size data (three or more points that correlate), use procedure 4A. - If you do not have sufficient estimated data but have sufficient plan added and modified and actual added and modified size data (three or more points that correlate), use procedure 4B. - If you have insufficient data or they do not correlate, use procedure 4C. - If you have no historical data, use procedure 4D. |
| 4A | Size Estimating Procedure 4A | - Using the linear-regression method, calculate theβ0and β1 parameters from the estimated proxy size and actual added and modified size data. - If the absolute value ofβ0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4B. |
| 4B | Size Estimating Procedure 4B | - Using the linear-regression method, calculate theβ0andβ1parameters from the plan added and modified size and actual added and modified size data. - If the absolute value of β0is not near 0 (less than about 25% of the expected size of the new program), orβ1is not near 1.0 (between about 0.5 and 2.0), use procedure 4C. |
| 4C | Size Estimating Procedure 4C | If you have any data on plan added and modified size and actual added and modified size, setβ0= 0 and β1 = (actual total added and modified size to date/plan total added and modified size to date). |
| 4D | Size Estimating Procedure 4D | If you have no historical data, use your judgment to estimate added and modified size. |

(continued)

| PROBE Script (continued) |  |  |
| --- | --- | --- |
| Step | Activities | Description |
| 5 | Time Estimating Procedure | - If you have sufficient estimated proxy size and actual development time data (three or more points that correlate), use procedure 5A. - If you do not have sufficient estimated size data but have sufficient plan added and modified size and actual development time data (three or more points that correlate), use procedure 5B. - If you have insufficient data or they do not correlate, use procedure 5C. - If you have no historical data, use procedure 5D. |
| 5A | Time Estimating Procedure 5A | - Using the linear-regression method, calculate theβ0andβ1 parameters from the estimated proxy size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5B. |
| 5B | Time Estimating Procedure 5B | - Using the linear-regression method, calculate theβ0andβ1 regression parameters from the plan added and modified size and actual total development time data. - Ifβ0is not near 0 (substantially smaller than the expected development time for the new program), orβ1is not within 50% of 1/(historical productivity), use procedure 5C. |
| 5C | Time Estimating Procedure 5C | - If you have data on estimated – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/estimated – total added and modified size to date). - If you have data on plan – added and modified size and actual development time, setβ0= 0 and β1 = (actual total development time to date/plan total added and modified size to date). - If you only have actual time and size data, setβ0= 0 and β1 = (actual total development time to date/actual total added and modified size to date). |
| 5D | Time Estimating Procedure 5D | If you have no historical data, use your judgment to estimate the development time from the estimated added and modified size. |
| 6 | Time and Size Prediction Intervals | - If you used regression method A or B, calculate the 70% prediction intervals for the time and size estimates. - If you did not use the regression method or do not know how to calculate the prediction interval, calculate the minimum and maximum development time estimate limits from your historical maximum and minimum productivity for the programs written to date. |

| Exit Criteria | - Completed estimated and actual entries for all pertinent size categories - Completed PROBE Calculation Worksheet with size and time entries - Plan and actual values entered on the Project Plan Summary |
| --- | --- |

| Code Review Script |  |
| --- | --- |
| Purpose | To guide you in reviewing programs |
| Entry Criteria | - A completed and reviewed program design - Source program listing - Code Review checklist - Coding standard - Defect Type standard - Time and Defect Recording logs |
| General | Do the code review with a source-code listing; do not review on the screen! |

| Step | Activities | Description |
| --- | --- | --- |
| 1 | Review | - Follow the Code Review checklist. - Review the entire program for each checklist category; do not try to review for more than one category at a time! - Check off each item as it is completed. - For multiple procedures or programs, complete a separate checklist for each. |
| 2 | Correct | - Correct all defects. - If the correction cannot be completed, abort the review and return to the prior process phase. - To facilitate defect analysis, record all of the data specified in the Defect Recording log instructions for every defect. |
| 3 | Check | - Check each defect fix for correctness. - Re-review all design changes. - Record any fix defects as new defects and, where you know the number of the defect with the incorrect fix, enter it in the fix defect space. |

| Exit Criteria | - A fully reviewed source program - One or more Code Review checklists for every program reviewed - All identified defects fixed - Completed Time and Defect Recording logs |
| --- | --- |